## Development Tasks
Requirement | Req Date | Status | Inprogress |  | Completed |  |  | Type of change | Notes/Comments | Statement Of Work
|  |  | Dev Start | Dev End | Test Start | Test End | Prod Date
Page 1 of Quotations is good. No changes are needed. Page 2 needs to be included with the following -.Study designs needs to be added to each product as a custom field. This needs to be added in page 2 for every product chosen. Study design description needs to be able to accept paragraphs, bullets, bold etc - all possible formatting.Alf to send a sample Quotation for the team to work on. | 2017-09-06 | Complete | 2017-09-22 | 2017-10-15 | 2017-10-15 | 2017-10-16 | 2017-10-17 | DataBase Trigger | Create a new file(PDF, word or Excel) for each product with detailed product description. This file should be merged with the quotation file when the quotation is printed.R&D by tamil. Fri call to discuss the result. | This trigger will update the detailed description from Product table to sales order line and change the Quotation XML . Table name:sale_order_line,product_template,product_product
User must not be able to delete seed data from the front end. Either check box must be disabled or the user must be given an error message after the delete action is checked | 2017-09-06 | Nice to have | [6 empty] | nice to have feature to be implemented when time permits
On the customer page and the pipeline page, the 'new message' button to be replaced by The 'send email' button in the same location as the 'new message ' icon. 'New message' and 'log an internal note' buttons to be commented out for now. Followers must be visible though. | 2017-09-18 | IN Progress | 2017-10-05 | 2017-10-30 |  |  |  | C.Module | Email_mailThread_button | This custom module has not yet moved to Dev and tested yet .
Flow of emails: Shanthy 9/19 Email from Odoo -> client =works fine. Client replies -> Odoo = works fine Odoo replies -> client = works fine Client replies back to Odoo = Does not come through. | 2017-09-18 | Complete | 2017-09-13 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-10 | Configuration | Deleted the sales team alias id and updated the Accountmngr@xenometricsllc.com id . | Deleted all the duplicate id's and created a unique id(Accountngrtest) under settings->email->aliases .
In send email module, if the followers check box is checked, then -to,CC and Bcc - all email ID's in these 3 places to be added as followers. If the followers check box is unchecked, then all email ID's in these 3 places to be unchecked. | 2017-10-03 | In Progress | 2017-10-05 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-27 | DataBase Trigger | We have done for adding only the CC Recipients to followers . And checkbox is defined for TO recipients only . Completed by writing Triggers on PostgresDB . | Trigger will update the partner to mail Followers table from partner_cc_rel table .
Emails sent to new customers have the View Partner¦unfollow link . This needs to be removed. | 2017-10-03 | Complete | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | Configuration | Settings->email->templates | Under "Notification Email" clcik edit and change it to code view and remove the necessary part .
Product code name visible in Quotations page | 2017-10-10 | Complete | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | Base Code Change | Code change is done on Sale Module Sale.py
Display Partner - Descending order by opportunity in Customer View | 2017-07-19 | Complete | 2017-07-26 | 2017-07-27 | 2017-08-06 | 2017-08-06 | 2017-08-08 | DataBase Trigger | Changes made on DB and it has been revoked back by Alfred on 14-Aug. | We have written a trigger fuction without knowig that opportunity filtering option is available in Odoo deafult . So we have revoked the Opportunity_count.Ths Filter can be found on the search box . Click
New button for Email/message on every Customer Including CC | 2017-05-28 | Complete | 2017-05-28 | 2017-06-19 | 2017-05-28 | 2017-06-19 | 2017-06-19 | C.Module | yb_mail_cc_bcc
Email - Signature Formating | 2017-05-28 | Complete |  |  | 2017-06-10 | 2017-06-16 | 2017-06-16 | Configuration | Line Spacing,signature Logo and Fonts
Email - signature Logo change | 2017-09-06 | Complete | 2017-09-07 | 2017-09-11 | 2017-09-11 | 2017-09-17 | 2017-09-18 | logo on the email signature is not visible | We have croped the logo according to its size and uploadedo on Xenommetrics server and called it using it path .
Email - Subject line | 2017-05-28 | Complete | 2017-09-06 | 2017-09-07 | 2017-09-19 | 2017-09-20 | 2017-09-21 | Base Code Change | Mail Module . Mail->Static->src->xml->thread.xml
QUOTATION CHANGES: Move the quotation number field to the top right just beneath the tag line | 2017-06-18 | Complete |  |  | 2017-06-18 | 2017-07-21 | 2017-07-21 | Configuration | Settings->reports ->Quotation. | Once clicking on Report search for "QUOTATION" . Later click on the Qweb that shows at the right corner and select the second option (report_saleorder_document) . Edit the Translation .
Move the customer’s address to beneath the quote number | 2017-06-18 | Complete |  |  | 2017-06-18 | 2017-07-21 | 2017-07-21 | Configuration | Settings->reports ->Quotation.
The word “sales person” to be replaced with “Account Manager” throughout the quote and anywhere in the CRM | 2017-06-18 | Complete |  |  | 2017-06-18 | 2017-07-21 | 2017-07-21 | Configuration | Settings->reports ->Quotation.
Delete the second occurrence of the payment terms. Leave the first one that appears next to the “Account Manager” after that word replaces “sales person” in 3 above. | 2017-06-18 | Complete |  |  | 2017-06-18 | 2017-07-21 | 2017-07-21 | Configuration | Settings->reports ->Quotation.
QUOTATION FOOTER : Add additional email addresses to the footer of the quotation templates | 2017-06-18 | Complete |  |  | 2017-06-18 | 2017-07-22 | 2017-07-22 | Configuration | Settings -> user Interface->Views | Search for "external_layout_footer" inside views and edit the Qweb .
Disable the followers Checkbox | 2017-09-06 | Complete | 2017-09-07 | 2017-09-07 | 2017-09-07 | 2017-09-07 | 2017-09-08 | C.module | Uninstall the Followers Module (Addon mail followers 063017) | This Module will add the followers of the particular customer automatically as Recipients in email .
Change ‘recipients’ label to ‘To’ like in any email. | 2017-09-06 | Complete | 2017-09-07 | 2017-09-07 | 2017-09-07 | 2017-09-07 | 2017-09-08 | Configuration | On Odoo server goto Settings-User Interface->Views | Under Views Search "mail.compose.message.form" . Edit Translations and rename recipients -> TO .
The ‘CC’ed and Bcc email(if any) to be shown in the email transactions under the page | 2017-09-06 | Complete | 2017-08-17 | 2017-09-18 | 2017-09-18 | 2017-09-20 | 2017-09-21 | C.Module | IT IS_MAIL_CC_BCC, | It is a customized module , that module contains javascript and kanban view(QWEB) updated the transaction data (CC,BCC).
sales person has to me notified whenever an opportunity is created |  | FREEZED
Odoo Server Crash | 2017-08-14 | Complete | 2017-08-14 | 2017-08-22 | 2017-08-25 | 2017-08-25 |  |  | One of the seed data has been deleted from base model | The seed data which is present in crm.team has been unfortunately deleted. The seed data is nothing but the Direct Sales which is a default data of CRM team.The CRM should contain the default data

## Regular tasks
Backup of code and Database | Last business day of the week
Keep track of all changes | Everyday
Production push backup of code and Database | Before every production push

## Backup Files
Date | Machine name | Path of the Backup file
2017-09-05 | Development Machine | C:\Users\ERPmanage\Downloads\Odoo-sw\DB_Backups
2017-08-29 | Developmment Machine | C:\Users\ERPmanage\Downloads\Odoo-sw\DB_Backups
2017-08-12 | Developmment Machine | C:\Users\ERPmanage\Downloads\Odoo-sw\DB_Backups
2017-10-17 | Production Machine | C:\Users\ERPmanage\Downloads
2017-08-31 | Production Machine | C:\Users\ERPmanage\Downloads